## Revised 11-14-13
DRAFT Worksheet For NRCC Planning/Discussion (11/15/2013)
| Scheduling Worksheet for Stock Assessments. | date: Nov. 14, 2013
| Basis for entries in Table: | May 2013 NRCC meeting and after
| 2013: 1st half | 2013: 2nd half
1 | White hake - SARC 56, Feb 19 -22, 2013 | Striped bass - SARC 57, [July 23-26]
2 | Atlantic surfclam - SARC 56 | Summer flounder - SARC 57
3
4
5
6
7 | (River herring - Extinction Risk Analysis) | (Data Review, August 5-9)
8 | (EGB cod benchmark - Ap. 9-11, 2013, TRAC)
9 | (TRAC - EGB cod, EGB haddock, GB YT - June 25-27 Canada)
10 | (Updates: Bluef, Scup [w/ SSC], Dog, skates, monkfish -Ap. 8-9 Op. Assess., Ocean quahog, Mackerel, butterfish, tilefish, squid
| 2014: 1st half | 2014: 2nd half
1 | N. shrimp - SARC 58, Jan. 27-31 | Scallops - SARC 59, July 15-18
2 | Tilefish - SARC 58 | Bluefish - SARC 59
3 | Butterfish - SARC 58
4
5
6 | (ASMFC - Sturgeon -Feb). | (Multisp. Groundfish Updates, Operational Assessment , Nov.)
7 | (GB YT Alternative OR Scallop Survey methods peer review - March)
8 | (ASMFC - Lobster peer review -April)
9 | (Model Review - May)
10 | (TRAC - EGB cod, EGB haddock, GB YT ) June 23 -27, WH
11
12 | (Updates: BlkSeaBass [research report], Scup [rumble strip], Fluke, Mackerel, squid | (Updates: Dog, skates, hakes (silver, red, offshore)
| 2015: 1st half | 2015: 2nd half
1 | GOM haddock - SARC 60 | Pollock - SARC 61
2 | squid (shortfin)- SARC 60 | Ocean quahog BRPs - SARC 61
3 | squid (longfin) - SARC 60
4
5 | (ASMFC - Sturgeon -Feb). | ( Research on Rapid Assessment Methods, rumble strips, sign posts) ???
6 | (TRAC - EGB cod, EGB haddock, GB YT - June)
7 | (Updates: Bluef, BlkSeaBass [product ???], Scup [product ???], Fluke, Dog, skates, Mackerel, butterfish, tilefish
| 2016: 1st half | 2016: 2nd half
1
2
3
4
5
6
7
Key:
Italics = Under consideration, but not officially scheduled.
"( )" = not in the SARC process.
| Cells filled with gray = work completed. | ~/sarc/boilerplate/Schedule-worksheet-assessments(date).xls 11/8/2013-b